Sprint 3 Week 1 Governance and Access Control Record

Task 61 - Sprint 3 Governance & Access Activation

| Project number | 74 |
| --- | --- |
| Project ID | P000785CSITCP |
| Project name | Building an Editor Academy Moodle platform |
| Client / organization | Open Access Publishing Association (OAPA) |
| Team | Team A |

Task and closeout position

| Role | PM - Aryan Rajendra | Date | 11/10/2026 |
| --- | --- | --- | --- |
| Sprint / Week | Sprint 3 / Week 1 | Hours | 2 |
| Track | Design / Product | Status | Finished |
| Planner task | Task 61 | Planned minutes | 120 |
| Sprint purpose | Refine MVP | Client response | Pending - approximately 1.5 weeks |

1. Purpose and completion position

This record establishes the final Sprint 3 Week 1 governance, access and evidence baseline from the Sprint 2 closeout position. Sprint 3 remains a Refine MVP sprint: the purpose is to harden the already demonstrated Core MVP, close verified-attendance, assessment, branding/navigation/accessibility, H5P/reporting and handover gaps, and avoid introducing unapproved feature expansion.

At Week 1 closeout, the client has not provided a new response for approximately 1.5 weeks. Team 74 has therefore continued implementation using a documented workaround: team members downloaded and installed a local Moodle development environment on their own desktop machines, providing direct access to Moodle code and configuration for development, testing and evidence capture. This local environment enables progress but does not constitute new OAPA approval or final deployment/validation in the hosted OAPA Academy.

2. Sprint 3 Week 1 governance baseline

Tasks 61-70 are the approved Sprint 3 Week 1 workload and remain aligned with the three-week Sprint 3 refinement plan.

Every Week 1 task is planned at 120 minutes; each team member owns two tasks for a total planned workload of 240 minutes.

Completed Sprint 2 Core MVP functionality is not reopened unless a new reproducible defect or acceptance gap justifies the change.

Existing client decisions continue to govern the product. No new client approval is inferred from silence or from what the local Moodle environment technically permits.

The new OAPA Academy remains the implementation target and the legacy Moodle remains reference-only.

Locally hosted Moodle copies are the current implementation workaround while OAPA-controlled site-level deployment and final hosted-environment verification remain external dependencies.

3. Access and environment control

| Area | Current position | Governance control |
| --- | --- | --- |
| Hosted OAPA Academy | Teacher/course-level access was previously verified. No new client response has been received for the Sprint 3 site-level position. | Do not claim new hosted-site permissions, deployment or approval until confirmed by OAPA. |
| Local Moodle workaround | Team members installed local Moodle development environments on their own desktops and now have direct code/configuration access for continued work. | Use local copies for development, controlled testing and evidence; retain a clear distinction from OAPA-hosted deployment. |
| Site-level functions | Themes/fonts, plugins, repositories, backend administration and other site-level actions remain OAPA-controlled in the actual Academy unless separately confirmed. | Record the exact capability or permission still required rather than a broad access blocker. |
| Legacy Moodle | Reference-only. | No implementation changes are to be made to the legacy site. |
| H5P / reporting | H5P Question Set was already confirmed working. Known staff-side reporting/Gradebook limitations remain separate from H5P creation/feedback behaviour. | Retain native Moodle Quiz fallback and re-verify site-specific reporting in the actual OAPA environment when available. |

4. Planner and Gantt alignment

| Task | Owner | Week 1 purpose | Planned | Closeout state |
| --- | --- | --- | --- | --- |
| 61 | Aryan Rajendra | Governance, access, evidence and review control | 120 min | Finished |
| 62 | Aryan Rajendra | Stakeholder implementation review and follow-up control | 120 min | Finished |
| 63 | Riley Pittard | Final requirements and acceptance baseline | 120 min | Completed |
| 64 | Riley Pittard | Workshop and assessment requirements control | 120 min | Completed |
| 65 | Walaa Ghanduri | Branding, navigation and accessibility handoff | 120 min | Completed |
| 66 | Walaa Ghanduri | Participants and learner-experience refinement | 120 min | Completed |
| 67 | Reshan Lahandapura | Verified workshop-attendance integration | 120 min | Completed |
| 68 | Reshan Lahandapura | Eligibility and assessment workflow hardening | 120 min | Completed |
| 69 | Shaikh Zarin Tasnim | Branding and navigation implementation | 120 min | Completed |
| 70 | Shaikh Zarin Tasnim | Cross-test and H5P quality closeout | 120 min | Completed |

5. Dependency and ownership register

| Dependency / control | Week 1 position | Owner / next action |
| --- | --- | --- |
| Client / OAPA response | No new response for approximately 1.5 weeks; no new decision or permission is claimed. | PM - retain follow-up trail and obtain explicit confirmation before claiming hosted deployment or approval. |
| Verified Teams attendance | Week 1 implementation and testing completed in the team-controlled Moodle development environment; hosted OAPA verification remains required. | Dev 1 / BA / Dev 2 - preserve evidence and re-validate in OAPA Academy when site-level route is available. |
| Assessment eligibility and workflow | Week 1 hardening completed against verified attendance and existing assessment rules in the development environment. | Dev 1 / BA / Dev 2 - re-run hosted-environment acceptance evidence after deployment. |
| Branding / fonts / navigation / accessibility | Implementation and feasibility work completed within currently controllable capability. | UX / Dev 2 - carry only exact unsupported site-level items to OAPA; do not treat local capability as hosted permission. |
| Participants refinements | Validated against Moodle-native capability and carried forward only where useful and feasible. | UX / Dev 2 - retain native functionality and avoid unnecessary recreation. |
| H5P / Gradebook / staff reporting | H5P working state remains confirmed; native Quiz remains fallback. Site-specific reporting/Gradebook limitations remain separate. | Dev 2 / Dev 1 / OAPA admin - re-test reporting in actual OAPA environment and escalate exact site-level issue if it persists. |
| Final evidence and handover | All Week 1 tasks require linked artefacts and truthful completion notes. | All owners - add final repository URLs; PM reconciles Planner, Gantt, Master Document and handover records. |

6. Evidence expectations and review checkpoints

Each task retains one scored owner, its 120-minute workload, completed acceptance checklist, completion notes, deliverable name and a direct Git/artifact URL.

Implementation claims must identify whether evidence comes from the locally hosted Moodle development environment or from the actual hosted OAPA Academy.

The Week 1 internal evidence closeout is completed before Planner tasks are moved to the Sprint 3 Week 1 completion bucket.

The stakeholder implementation review is recorded separately in Task 62. Client non-response is recorded as an external dependency, not converted into approval.

When OAPA responds, only the exact hosted-environment deployment/permission items still outstanding are reopened for verification; completed local development work is not repeated without reason.

7. Decisions and scope controls

| Control | Week 1 decision |
| --- | --- |
| Sprint definition | Sprint 3 remains Refine MVP rather than feature expansion. |
| Client authority | Existing confirmed client decisions remain governing; no new decision is fabricated from the current response gap. |
| Local environment | Approved as the team workaround for continued development/testing; it is not treated as evidence of new OAPA-hosted permissions. |
| Core MVP reopening | Completed Sprint 2 work is changed only when Week 1 evidence identifies a genuine defect or required refinement. |
| Evidence discipline | Planner, Gantt, Master Document, repository artefacts and review records must describe the same implementation state. |

8. Completion statement

Task 61 is complete as the Sprint 3 Week 1 governance and access-control baseline. The team has a documented route for continuing implementation through local Moodle environments while maintaining the required separation between team-controlled development and OAPA-controlled hosted deployment. The current client response gap, exact site-level dependencies, Week 1 ownership, evidence requirements and review checkpoints are recorded without expanding Core MVP scope or claiming approvals that have not been received.

Repository target: https://github.com/S4090860/Team-74---Building-an-Editor-Academy-Moodle-platform---Team-A/blob/main/Sprint%203/Week%201/Aryan%20Rajendra%20-%20Project%20Manager/Sprint3Week1GovernanceAccessControlRecord.docx