## Instructions
Sprint Planning — Instructions & Legend
COSC2408 Programming Project 1
What this workbook is for
This is the detailed HOW for next sprint — the task-by-task breakdown, owner, timing and sequencing. It is a separate deliverable from your Sprint Playback slide 7 ("What's Next"), which only states WHAT you're promising. This workbook is where that promise gets broken down into real, assigned, time-estimated tasks.
The 240-minute rule
Every team member must be assigned at least 240 minutes (4 hours) of tasks per week, for every week of the upcoming sprint. Estimate time at a junior-practitioner level — the same standard used for your weekly task board (e.g. a straightforward API endpoint with tests is ~30 minutes, regardless of how long it actually takes you in practice). The Weekly Workload Check tab totals this automatically and flags anyone under the minimum.
How to use the Task Plan & Gantt tab
1. Delete the yellow example row once you understand the format — it is not a real task.
2. Add one row per task: name it, assign an Owner, estimate the minutes, set the Week (1–3), the Start Day WITHIN that week (1 = Monday, 5 = Friday) and the Duration in days.
3. The Gantt bar on the right fills in automatically based on Start Day and Duration — you don't edit it directly.
4. Use Dependencies to note if a task can't start until another Task ID is done.
5. Update Status as the sprint progresses — this tab doubles as your working plan, not just a one-off submission.
Editable vs computed
Only the white cells in the Task Plan & Gantt tab are for you to fill in (Task ID through Status). The Gantt bars and everything on the Weekly Workload Check tab are computed automatically — don't type into them. You can change the roles by maunally typing into Column C (owner) and then using the same valueein the Weekly Workload check
Submission
Rename this file x - team name - S1W7_ganttplan (e.g. 90 - Food Delivery System - S1W7_ganttplan) and submit alongside your other Week 7 files. It plans the upcoming sprint, so it's due the same week as your Playback.
Colour key
Example row — delete before submitting
Weekly Workload Check: meets the 240-minute minimum
Weekly Workload Check: under the 240-minute minimum

## Task Plan & Gantt
Team 74 — Next-Sprint Task Plan & Gantt ¦ Sprint 3 (Weeks 1–3)
Every member needs ≥240 min/week. See the Instructions tab before editing.
Task ID | Task Name | Owner | Est. Minutes | Week | Start Day (1=Mon–5=Fri) | Duration (days) | Dependencies | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
[8 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
T61 | [SPRINT 3 GOVERNANCE & ACCESS ACTIVATION] - Task 61 Initialise Sprint 3 Refine MVP in Planner/Gantt and control the isolated-Academy-copy, site-level dependencies, evidence expectations and review checkpoints: 120 | Aryan Rajendra | 120 | 1 | 1 | 1 | T52,T54,T56,T58,T60
T62 | [SPRINT 3 STAKEHOLDER IMPLEMENTATION REVIEW] - Task 62 Run the Week 1 client/supervisor implementation checkpoint and record decisions, completed site-level work, remaining blockers and agreed Sprint 3 follow-up actions: 120 | Aryan Rajendra | 120 | 1 | 4 | 1 | T61,T64,T66,T67,T69
T63 | [SPRINT 3 FINAL REQUIREMENTS BASELINE] - Task 63 Convert the Sprint 2 closeout gaps and confirmed client decisions into the final Sprint 3 implementation and acceptance baseline: 120 | Riley Pittard | 120 | 1 | 1 | 1 | T53,T54
T64 | [SPRINT 3 WORKSHOP & ASSESSMENT REQUIREMENTS CONTROL] - Task 64 Finalise implementation criteria for verified Teams workshop attendance, two-of-three eligibility and the complete assessment workflow without introducing unapproved behaviour: 120 | Riley Pittard | 120 | 1 | 2 | 1 | T63
T65 | [SPRINT 3 BRANDING NAVIGATION & ACCESSIBILITY HANDOFF] - Task 65 Issue the final implementation-ready UX handoff for OAPA branding/fonts, navigation, signposting and accessibility in the isolated Academy environment: 120 | Walaa Ghanduri | 120 | 1 | 1 | 1 | T56
T66 | [SPRINT 3 PARTICIPANTS & LEARNER EXPERIENCE REFINEMENT] - Task 66 Validate the Participants-tab mock-ups and remaining learner/staff UX refinements against native Moodle capability; issue only feasible implementation changes: 120 | Walaa Ghanduri | 120 | 1 | 2 | 1 | T65
T67 | [SPRINT 3 WORKSHOP ATTENDANCE INTEGRATION] - Task 67 Implement the live Teams workshop and verified-attendance workflow in the isolated Academy copy and connect verified attendance to the existing two-of-three assessment-eligibility logic: 120 | Reshan Lahandapura | 120 | 1 | 3 | 1 | T61,T63,T64,T65
T68 | [SPRINT 3 ELIGIBILITY & ASSESSMENT WORKFLOW HARDENING] - Task 68 Integrate verified workshop attendance with final assessment eligibility and harden the soft-feedback, revision, direct-final, extension and grade-release workflow: 120 | Reshan Lahandapura | 120 | 1 | 4 | 1 | T64,T67
T69 | [SPRINT 3 BRANDING & NAVIGATION IMPLEMENTATION] - Task 69 Apply the approved OAPA branding/fonts and feasible navigation/accessibility changes in the isolated Academy copy using Moodle-native or approved site-level capability: 120 | Shaikh Zarin Tasnim | 120 | 1 | 3 | 1 | T61,T65,T66
T70 | [SPRINT 3 WEEK 1 CROSS-TEST & H5P CLOSEOUT] - Task 70 Independently cross-test the workshop, assessment, branding and navigation changes and close the final H5P Question Set status with the Moodle-native fallback retained: 120 | Shaikh Zarin Tasnim | 120 | 1 | 5 | 1 | T67,T68,T69
T71 | [SPRINT 3 MID-SPRINT STAKEHOLDER REVIEW] - Task 71 Run the mid-Sprint 3 client/Vic review against the implemented Week 1 changes and record accepted fixes, blockers and final refinement decisions: 120 | Aryan Rajendra | 120 | 2 | 4 | 1 | T70,T73,T75,T77
T72 | [SPRINT 3 GOVERNANCE RISK & EVIDENCE CONTROL] - Task 72 Update risks, decisions, Planner/CRM evidence and the refinement backlog after the mid-sprint review; preserve a clear route to final handover: 120 | Aryan Rajendra | 120 | 2 | 5 | 1 | T71,T80
T73 | [SPRINT 3 END-TO-END ACCEPTANCE VALIDATION] - Task 73 Validate the implemented learner, workshop, assessment, tracking and content-expert reuse journeys against the final Sprint 3 acceptance baseline: 120 | Riley Pittard | 120 | 2 | 1 | 1 | T68,T70
T74 | [SPRINT 3 SCOPE & DEFERRED REQUIREMENTS CONTROL] - Task 74 Finalise the accepted, deferred, OAPA-admin and out-of-scope requirement register so the team can close the project without hidden scope gaps: 120 | Riley Pittard | 120 | 2 | 2 | 1 | T73
T75 | [SPRINT 3 IMPLEMENTED UX & ACCESSIBILITY REVIEW] - Task 75 Review the refined real-Academy build across Course Home, modules, workshops, assessment, Participants and learner progress; issue evidence-based final UX corrections: 120 | Walaa Ghanduri | 120 | 2 | 1 | 1 | T69,T70
T76 | [SPRINT 3 FINAL UX REFINEMENT HANDOFF] - Task 76 Refine the feasible Participants, navigation, responsive and accessibility treatment after real-build review and hand off only implementation-ready corrections: 120 | Walaa Ghanduri | 120 | 2 | 2 | 1 | T73,T75
T77 | [SPRINT 3 DEFECT FIXING & REGRESSION] - Task 77 Fix functional defects from integrated acceptance and UX review across progression, workshop attendance, eligibility, assessment and navigation; regression-test the corrections: 120 | Reshan Lahandapura | 120 | 2 | 3 | 1 | T73,T75
T78 | [SPRINT 3 REUSE DUPLICATION & CONTENT-EXPERT VALIDATION] - Task 78 Prove the reusable-template workflow in the isolated copy and validate the content-expert versus OAPA-admin duplication/site-level handoff without altering the master pattern: 120 | Reshan Lahandapura | 120 | 2 | 4 | 1 | T74,T77
T79 | [SPRINT 3 COMPATIBILITY & ACCESSIBILITY REGRESSION] - Task 79 Run browser, responsive-device, keyboard and accessibility regression on the refined Academy experience and independently re-test Dev 1 fixes: 120 | Shaikh Zarin Tasnim | 120 | 2 | 4 | 1 | T76,T77
T80 | [SPRINT 3 WORKFLOW TRACKING & QUALITY CLOSEOUT] - Task 80 Cross-test completion, reporting, workshop/assessment edge cases and returning-learner behaviour; close H5P/native-fallback and Week 2 quality evidence: 120 | Shaikh Zarin Tasnim | 120 | 2 | 5 | 1 | T77,T78,T79
T81 | [SPRINT 3 FINAL CLIENT SUPERVISOR ACCEPTANCE] - Task 81 Run the final client and Vic acceptance/handover review; record accepted deliverables, unresolved OAPA-admin actions and final project decisions: 120 | Aryan Rajendra | 120 | 3 | 4 | 1 | T83,T85,T87,T89
T82 | [SPRINT 3 PROJECT EVIDENCE & HANDOVER CLOSEOUT] - Task 82 Consolidate final Planner, CRM, playback, decision, testing and handover evidence and prepare the complete project closeout/submission package: 120 | Aryan Rajendra | 120 | 3 | 5 | 1 | T81,T84,T86,T88,T90
T83 | [SPRINT 3 FINAL ACCEPTANCE TRACEABILITY] - Task 83 Run the final requirement-by-requirement acceptance check and produce the final traceability position for the delivered OAPA Academy framework: 120 | Riley Pittard | 120 | 3 | 1 | 1 | T78,T80
T84 | [SPRINT 3 FINAL SCOPE & REQUIREMENTS HANDOVER] - Task 84 Finalise the delivered/deferred/admin requirement register and prepare the requirements handover for OAPA future course reuse and maintenance: 120 | Riley Pittard | 120 | 3 | 2 | 1 | T83
T85 | [SPRINT 3 FINAL UX BRAND & ACCESSIBILITY SIGN-OFF] - Task 85 Complete the final UX, OAPA Brand Book, navigation, responsive and accessibility sign-off against the release candidate: 120 | Walaa Ghanduri | 120 | 3 | 1 | 1 | T79,T80
T86 | [SPRINT 3 UX & CONTENT-EXPERT HANDOVER] - Task 86 Prepare the final UX/content-expert handover showing how future OAPA course authors should preserve navigation, branding, accessibility and learner-flow patterns when reusing the framework: 120 | Walaa Ghanduri | 120 | 3 | 3 | 1 | T84,T85
T87 | [SPRINT 3 RELEASE-CANDIDATE DEFECT CLOSURE] - Task 87 Apply final accepted functional fixes, regression-test the release candidate and freeze the implemented reusable framework for handover: 120 | Reshan Lahandapura | 120 | 3 | 2 | 1 | T83,T85
T88 | [SPRINT 3 OAPA ADMIN & REUSE HANDOVER] - Task 88 Finalise the technical reuse, duplication and OAPA-admin site-level handover guide for safely creating future courses from the master framework: 120 | Reshan Lahandapura | 120 | 3 | 3 | 1 | T86,T87
T89 | [SPRINT 3 FINAL INDEPENDENT REGRESSION] - Task 89 Independently run the final release-candidate regression from Student and Teacher views across progression, attendance, assessment, tracking, navigation and accessibility: 120 | Shaikh Zarin Tasnim | 120 | 3 | 4 | 1 | T87,T88
T90 | [SPRINT 3 TECHNICAL QUALITY HANDOVER] - Task 90 Close final test evidence, environment assumptions, H5P/native-fallback status, known limitations and technical quality handover for OAPA: 120 | Shaikh Zarin Tasnim | 120 | 3 | 5 | 1 | T88,T89

## Weekly Workload Check
Weekly Workload Check — 240 min (4 hrs) minimum per person, per week
Computed automatically from the Task Plan & Gantt tab. Do not edit the numbers directly.
Role | Week 1 (min) | Week 2 (min) | Week 3 (min) | Sprint Total (min) | Sprint Total (hrs)
Aryan Rajendra | 240 | 240 | 240 | 720 | 12
Riley Pittard | 240 | 240 | 240 | 720 | 12
Walaa Ghanduri | 240 | 240 | 240 | 720 | 12
Reshan Lahandapura | 240 | 240 | 240 | 720 | 12
Shaikh Zarin Tasnim | 240 | 240 | 240 | 720 | 12
Green = meets the 240-minute weekly minimum. Red = under the minimum — rebalance tasks in the Task Plan & Gantt tab.