Risk, Dependency, Escalation & Communication Register

Sprint 1 governance artifact - updated to current client/access situation and OAPA specification

| Project | P000785CSITCP / Group 74 Team A | Owner | Aryan Rajendra - Project Manager |
| --- | --- | --- | --- |
| Status | Updated / active register | Current as of | 23 August 2026 |

# 1. Current governance position

The original access blocker is still active, but the stakeholder situation has changed. Darryl is no longer classified simply as an unresponsive client, on 21 August he advised that he is in hospital and expects to be unavailable for another week. OAPA project continuity is now being supported by Professor Michael Cowling and Jo-Anne Kelder. Jo provided the OAPA Moodle specification and directed Team 74 to Sam via tech@open-publishing.org for Moodle access. An access request for the current Academy page and old Moodle page has been sent and remains pending.

No unsupported date This register does not claim that Moodle access will arrive on a particular date. Access remains a dependency until Sam/OAPA confirms it and Team 74 verifies the actual permission level.

# 2. Active risk register

| ID | Type | Risk / issue | Status | Rating | Owner | Mitigation / next action |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Access | Current/old Moodle access not yet provided | Active | High | Aryan + Reshan | Keep access-independent work moving, access request sent to Sam, verify account/permissions immediately on receipt, record evidence in Planner. |
| R2 | Environment | Editable sandbox/change workflow not confirmed | Active | High | Reshan + Aryan | No production changes. Confirm read-only vs edit access, sandbox location, theme/plugin permissions, source-control and approval workflow before implementation. |
| R3 | Stakeholder availability | Primary client contact unavailable due hospital stay | Active / mitigated | Med-High | Aryan | Use Michael and Jo for project continuity, route technical access to Sam, keep Darryl informed without relying on him for immediate action while unavailable. |
| R4 | Schedule | Sprint 1 slippage caused by extended access delay | Active | High | Aryan | Prioritise specification review, requirements, proposed UX, Moodle research and planning in parallel, document blocked tasks, re-sequence access-dependent work once access arrives. |
| R5 | Scope | Broader OAPA specification may exceed Team 74 proposal boundary | Active | High | Aryan + Riley | Treat broad capabilities as target-state requirements, confirm Team 74 implementation subset with Michael/Jo/Vic before committing Sprint 2 scope, maintain explicit out-of-scope list. |
| R6 | Requirements | Specification arrived after Sprint 1 work had started | Active | Medium | All / Aryan coordinates | Cross-check existing artifacts against the specification, add missing items only, do not force unnecessary rework where existing research already aligns. |
| R7 | Branding | Final OAPA branding/theme guidance not confirmed | Open | Medium | Walaa + Aryan | Use professional academic provisional direction, label as proposed, request final assets/constraints before high-fidelity sign-off. |
| R8 | Technical feasibility | Soft/hard deadline workflow is not a single default Moodle field | Open | Med-High | Reshan + Zarin | Prototype/verify Moodle mechanism and grade-visibility behaviour, document trade-offs before implementation commitment. |
| R9 | Technical feasibility | Peer-review anonymity/editorial workflow mechanism may require configuration/plugin decisions | Open | Medium | Zarin + Reshan | Assess native Workshop/other suitable mechanisms, confirm anonymity defaults and editorial outcomes with client. |
| R10 | Architecture | Expected scale and international learner profile are not fully confirmed | Open | Medium | Riley + Reshan | Record as assumptions, confirm cohort size/concurrency and likely learner locations before architecture/reporting decisions are finalised. |
| R11 | Quality | Current-state UX claims could be made without live platform evidence | Controlled | Medium | Walaa + Aryan | Label proposed journeys/recommendations as proposed until verified, PM reviews wording before sign-off. |
| R12 | Confidentiality | OAPA specification is marked confidential | Controlled | Medium | All / Aryan | Keep document and derivative evidence in authorised Teams/project locations, do not publish confidential content to public repositories. |
| R13 | Approval | Client proposal / exact Sprint 2 MVP still requires stakeholder alignment | Open | Medium | Aryan | Use next client meeting to confirm representative MVP and any scope changes, record decision and update Planner/decision log. |

# 3. Dependency register

| ID | Dependency | External / internal owner | Current state | Impact | Required action |
| --- | --- | --- | --- | --- | --- |
| D1 | Moodle account access | Sam / OAPA technical | Current and old Moodle pages requested 21 Aug | Blocking current-state audit and environment verification | Awaiting response, verify immediately when supplied |
| D2 | Sandbox/edit permissions | OAPA technical | Not yet confirmed | Blocking safe implementation | Confirm separate safe edit environment and change approval process |
| D3 | Scope interpretation of OAPA brief | Michael / Jo / Vic | Not fully confirmed | Can cause Sprint 2 over-commitment or scope drift | Confirm which target capabilities Team 74 must implement vs only design/research |
| D4 | Exemplar course/content | OAPA education/content team | Client content exists, exact exemplar not confirmed | Needed for representative MVP | Confirm which Foundations/old course is the reference journey |
| D5 | Brand/theme guidance | OAPA stakeholders | Not final | Affects high-fidelity UX direction | Request assets/constraints before final prototype sign-off |
| D6 | Moodle mechanisms/plugins | OAPA technical + Dev team | Unknown until access/research | Affects H5P, workshop, assessment and peer-review feasibility | Verify installed/current capability, prefer native/minimal plugin approach |
| D7 | Stakeholder availability | Michael / Jo / Darryl | Alternative contacts active, Darryl unavailable | Affects decisions and sign-off | Use Michael/Jo now, schedule client alignment session, do not wait solely on Darryl |
| D8 | Team artifact alignment | All roles | Specification received mid-sprint | Can create inconsistent assumptions across BA/UX/Dev work | Each member cross-checks existing artifact against scope baseline and specification |

# 4. Escalation path

| Trigger | Escalate to | Channel | Owner | Required record |
| --- | --- | --- | --- | --- |
| Routine client/project question | OAPA project contacts | Email / agreed Teams meeting | Aryan PM | Record decision/action in Planner or project decision log. |
| Moodle access / technical permission | Sam via tech@open-publishing.org | Email | Aryan PM, Reshan supplies technical details if needed | If unresolved before the next sprint-critical activity, escalate to Michael/Jo and inform Vic. |
| Primary client unavailable | Michael Cowling + Jo-Anne Kelder | Email / online client meeting | Aryan PM | Continue through alternate OAPA contacts rather than repeatedly chasing Darryl while he is unavailable. |
| Scope or requirement conflict | Michael/Jo + Vic | Client/supervisor meeting | Aryan + Riley | Do not implement disputed scope, record open decision and obtain confirmation. |
| Project blocker threatens course delivery/assessment | Vic, Nhi, Alessio / course support | Supervisor email/meeting, PM channel, support form | Aryan PM | Provide dated evidence of attempts, impact and mitigation. Avoid unsupported claims or blame. |
| Internal team dependency | Relevant role owner + PM | Teams + Planner | Aryan PM | Re-sequence work, run tasks in parallel where possible, only create hard dependencies where truly required. |

# 5. Communication and evidence register

| Date | Event | People / channel | Outcome / current state | Evidence |
| --- | --- | --- | --- | --- |
| 11 Aug 2026 | Initial client meeting | Darryl Clare + Team 74 | Scope focused on learner-facing UX, backend already established, read-only access then sandbox discussed, access expected the following day. | Meeting transcript / proposal |
| 14 Aug 2026 | Access follow-up | Darryl / Team 74 | Access still not received, blocker recorded transparently in proposal. | Email + proposal |
| By 19 Aug 2026 | Repeated follow-ups and course escalation | Darryl, Alessio/Nhi, course support | Four client follow-up emails had gone unanswered, team continued access-independent research and sought guidance instead of idling. | Email chain, PM-channel posts, support record |
| Escalation period | Additional contact attempts | Alessio / Darryl | PM also documented attempted in-person course contact and attempted client phone contact, blocker evidence preserved. | Teams evidence posts |
| 21 Aug 2026 | OAPA continuity check-in | Professor Michael Cowling | Michael contacted the team, explained Darryl had been on leave/in hospital and brought additional OAPA contacts into the project. | Email thread |
| 21 Aug 2026 | Client status update | Darryl Clare | Darryl confirmed he is in hospital receiving IV antibiotics and expects to be unavailable for another week. | Email thread |
| 21 Aug 2026 | Specification & access route | Jo-Anne Kelder | Jo sent the OAPA Moodle specification and directed Team 74 to Sam via tech@open-publishing.org for Moodle access. | Email + specification document |
| 21 Aug 2026 | Moodle access request | Sam / OAPA technical | Requested access to both the current Academy Moodle page and the old Moodle page, as suggested by Michael. | Sent email |
| 21 Aug 2026 | Client meeting coordination | Michael / Jo / Team 74 | 2,00 PM Monday 24 Aug proposed online, Michael had offered 2,00 PM in person, but Team 74 clarified the available members can attend online only. | Email thread, confirmation pending |
| Weekly | Supervisor governance | Vic Ciesielski | Recurring supervisor meeting booked Thursdays at 2,30 PM, use to report blockers, decisions and sprint progress. | Calendar/Teams meeting |

# 6. Communication rules for the team

Aryan (PM) is the single coordination point for external stakeholder follow-ups unless another team member is specifically asked to respond.

Important client/supervisor decisions are summarised in Teams and reflected in Planner/decision logs so the team works from one version of truth.

No task is marked complete until its checklist is genuinely satisfied and a completion/handoff note plus real evidence link is recorded.

Do not repeatedly chase an unavailable stakeholder when an escalation route exists. One clear follow-up should be followed by escalation through the agreed project/course contacts when the blocker threatens sprint progress.

Any statement about the existing Moodle configuration must be evidence-based after access, otherwise label it proposed, assumed or to be confirmed.

The confidential OAPA specification and derivative details stay in authorised project spaces.

# 7. Immediate action list

| ID | Action | Owner | Status |
| --- | --- | --- | --- |
| A1 | Monitor Sam/OAPA technical response for current and old Moodle access, do not promise an access date. | Aryan | Open |
| A2 | When access is received, Reshan verifies permission level, environment, theme/plugin constraints and sandbox readiness before any change. | Reshan + Aryan | Pending D1 |
| A3 | Use the next client alignment meeting to confirm Team 74's implementation subset of the OAPA specification and the representative Sprint 2 MVP. | Aryan + Riley | Pending meeting |
| A4 | All members cross-check already-started Sprint 1 artifacts against the OAPA specification and scope baseline, update only what is missing or contradicted. | All | In progress |
| A5 | Continue access-independent Sprint 1 research/design in parallel and clearly flag blocked work. | All | In progress |
| A6 | Report access/schedule status at the next Thursday 2,30 PM supervisor meeting and record any guidance. | Aryan | Scheduled |

# 8. Planner acceptance checklist mapping

| Checklist item | Evidence in this artifact |
| --- | --- |
| Moodle access recorded as an active blocker | Satisfied - R1/D1 and the communication register show access is still pending. |
| Client responsiveness dependency recorded | Satisfied and updated - R3/D7 records Darryl's temporary unavailability and the alternative OAPA contact path. |
| Impact on scheduled work explained | Satisfied - R4 records Sprint 1 slippage and identifies which work is blocked vs still progressing. |
| Mitigation actions documented | Satisfied - R1-R6, Sections 3 and 7 record access-independent work, cross-checking and re-sequencing actions. |
| Escalation and support actions documented | Satisfied - Section 4 and the communication register record course/OAPA escalation paths and completed support actions. |
| No unsupported claim that access will arrive by a particular date | Satisfied - access is explicitly recorded as pending with no promised delivery date. |

# 9. PM completion note for this update

This register reflects the current state rather than the earlier "unresponsive client" snapshot. The historical non-response remains documented as evidence of the delay, but the current dependency is stakeholder availability and access coordination through OAPA's alternate contacts. The access blocker remains active until Team 74 actually receives and verifies Moodle access.