Sprint 2 Week 2 Build Review & Stakeholder Alignment Record

Task 41 - Mid-sprint client/supervisor build review, decisions, open items and follow-up actions

| Project | P000785CSITCP / Group 74 - Team A | Owner | Aryan Rajendra - Project Manager |
| --- | --- | --- | --- |
| Status | Final / Task 41 completion evidence | Current as of | 26 September 2026 |

# 1. Purpose and review context

This record captures the Sprint 2 Week 2 stakeholder build review for Team 74 and converts the latest client decisions into an implementation handoff. The review was grounded in the real OAPA Academy development course, the Week 1 Core MVP evidence, the Week 2 developer build, the UX build review, and the client meeting held on 24 September 2026.

The client meeting with Michael Cowling and Jo-Anne Kelder was used as the primary Week 2 stakeholder review. The team demonstrated the current prototype in Student view, including the reusable three-module structure, sequential restrictions and the two-of-three workshop eligibility logic. The client response to the current direction was positive, while several workflow and site-level requirements were clarified for the remaining Sprint 2 implementation.

A separate supervisor meeting was not required this week because there were no supervisor-side questions or unresolved matters needing Vic Ciesielski's clarification. The PM notified Vic of the project status and confirmed that the client meeting would still proceed. Any issue that becomes a supervisor-level delivery risk will be escalated through the normal governance route.

Scope control: Sprint 2 remains focused on one representative reusable OAPA Academy course framework. New client clarifications refine the existing Core MVP and do not authorise expansion into a full Academy rebuild, new backend infrastructure or unrelated platform work.

# 2. Current build position reviewed

| Review area | Current status | Evidence / observed state | Week 2 follow-up |
| --- | --- | --- | --- |
| Reusable course shell | Working | Course Home/general area, Modules 1-3, Workshops 1-3 and the Assessment area are present in the Team 74 development course. | Keep the shell reusable and separate from course-specific academic content. |
| Sequential progression | Working / client-confirmed default | Current restrictions prevent learners from skipping required prior content. Later content can remain visible but restricted. | Keep sequential progression as the default while allowing facilitator configuration where Moodle supports it. |
| Workshop eligibility | Logic working; attendance source not final | The Assessment can remain locked with zero/one workshop and unlock after any valid two-of-three workshop combination. | Replace interim learner self-completion with a verifiable attendance source and manual exception route. |
| Self-check / quiz | Working | A Moodle-native Quiz/self-check pattern is available and H5P Question Set support has been re-opened after Sam installed the missing content type. | Zarin to re-test H5P; keep native Quiz as a valid fallback. |
| Assessment workflow | Partially implemented | Soft/hard dates, resubmission, extension and grade visibility have been prototyped in the real Academy. | Align final behaviour with the client decision on soft feedback, pass/fail marking and facilitator discretion for late cases. |
| Learner progress | Working at course level | Completion and locked/unlocked states are visible and persist through the learner journey. | Complete Week 2 reporting verification from learner and staff views. |
| UX / branding | UX review complete; site theming outstanding | UX reviewed the real build. OAPA Brand Book treatment is not yet fully applied because theme-level controls sit outside normal Teacher permissions. | Apply feasible course-level corrections and progress the site-level theme/access request with Sam. |

# 3. Client decisions confirmed on 24 September 2026

| Decision area | Client clarification | Implementation consequence |
| --- | --- | --- |
| Online workshop delivery | Workshops are live online sessions. OAPA previously used Zoom links embedded in Moodle and now intends to use MS Teams links. | Represent the workshop clearly in Moodle and link learners to the live Teams session rather than treating it as ordinary static content. |
| Workshop attendance evidence | OAPA wants a verifiable record of actual attendance and prefers automated recording where possible. Manual override should remain available for exceptional cases. | Investigate Teams attendance/Moodle integration or an OAPA-supported attendance mechanism; retain a staff override route. |
| Workshop hurdle | Learners must attend at least 2 of the 3 workshops before becoming eligible for the assessment. | Keep the already-proven two-of-three access logic and connect it to the final attendance record. |
| Attendance quality | Attendance is about being present for the session rather than level of interaction. OAPA indicated that staying for the majority of the workshop can be used as a practical attendance criterion. | Final attendance process should be capable of supporting a defensible attendance record rather than learner self-certification. |
| Reusable template structure | The three-module structure is a useful default, but the template should be flexible for shorter, longer, face-to-face or hybrid offerings. | Do not hard-code the framework so that only exactly three modules can ever be used. |
| Module progression | Progression should be configurable by facilitators. The preferred default is sequential access, with later modules restricted until prior requirements are met. | Keep sequential restrictions as the default pattern but document how a facilitator can adapt them. |
| Assessment grading | Assessment is pass/fail. There is no late penalty model. | Do not implement percentage penalties for lateness. |
| Soft deadline | Learners may submit before the soft cutoff to receive facilitator feedback and then revise before the hard deadline. The soft cutoff must leave enough time for feedback and revision. | Configure the representative feedback/revision route and document the soft cutoff as configurable. |
| Hard deadline / late cases | The hard date is the policy deadline, but late cases may still be accepted at the facilitator's discretion. OAPA wants flexibility for individual circumstances. | Do not permanently hard-close the workflow in a way that prevents the agreed facilitator discretion. |
| Branding and theming | The prototype still needs OAPA branding applied in line with the Brand Book. | Site-level theme/access support has been requested from Sam for typography, black/white styling and signature treatment. |

# 4. Prototype review and stakeholder feedback

During the meeting, the current prototype was demonstrated from the learner perspective. The demonstration covered the three-module reusable structure, visible restrictions, step-by-step progression and the assessment restriction based on completion of any two workshops. The client accepted the direction of the prototype and responded positively to the reusable-template concept.

Michael specifically asked about the OAPA theming/branding that had appeared in earlier design work. The team confirmed that branding against the OAPA Brand Book remains part of the implementation and will be progressed as site-level access/support becomes available. The client also confirmed that the reusable template should remain configurable rather than being limited permanently to one fixed three-module format.

# 5. Open items and implementation corrections

| ID | Open item | Priority | Current evidence | Owner | Required action |
| --- | --- | --- | --- | --- | --- |
| A1 | Workshop attendance mechanism | High | Current Task 47 build uses learner self-marking as an interim stand-in. This is not the final client-approved attendance record. | Reshan + Aryan | Preserve two-of-three logic; replace interim completion source once Sam confirms the supported site-level route. |
| A2 | Assessment late-case behaviour | High | Current Task 48 prototype uses a hard cutoff that stops submissions after the date, while the client requires facilitator discretion for exceptional late cases. | Reshan + Riley | Adjust the workflow so the policy deadline is retained without removing facilitator discretion. |
| A3 | Soft feedback/final path | High | The client clarified that early soft submission is for feedback/revision, while learners who skip the soft route can submit final by the hard date but do not receive another resubmission opportunity. | Reshan + Riley + Zarin | Validate the exact Student/Teacher workflow and cross-test both paths. |
| A4 | UX documentation alignment | Medium | The current UX build review contains a Module 4 concept and an 80% quiz threshold assumption that are not confirmed client requirements. | Walaa + Riley | Keep Assessment separate from the module count and do not lock in a quiz threshold unless confirmed. |
| A5 | Brand Book implementation | Medium-High | Full OAPA theme treatment is not available through ordinary Teacher controls. | Walaa + Devs + Aryan | Implement feasible course-level treatment; track site-level access/support request with Sam. |
| A6 | H5P Question Set re-test | Medium / optional | Sam has installed the Question Set content type from the official H5P library; the team has not yet documented a successful re-test in the Week 2 repository. | Zarin | Re-test in the real Academy and document the result. Native Quiz remains a valid Core MVP fallback. |
| A7 | Staff reporting verification | Medium | Course-level progress works, but Week 2 staff-side reporting verification is still required. | Zarin | Complete Task 49 with learner/test-state and Teacher-side evidence. |

# 6. Agreed follow-up actions and owners

| Owner | Week 2 follow-up |
| --- | --- |
| Aryan / PM | Maintain the current Planner/risk baseline; track the site-level attendance and Brand Book requests sent to Sam; escalate only exact evidenced blockers. |
| Riley / BA | Update final workflow criteria to match the 24 September client decisions, especially attendance, assessment deadlines, late-case discretion and reusable-template flexibility. |
| Walaa / UX | Review the implemented learner journey, correct the Module 4/mandatory workshop assumptions, and specify Brand Book corrections that can be implemented now versus site-level changes. |
| Reshan / Dev 1 | Keep the two-of-three gate, replace interim attendance completion when the supported route is confirmed, and align the assessment configuration with the client deadline decisions. |
| Zarin / Dev 2 | Re-test H5P after Sam's fix, verify learner/staff reporting, and independently cross-test attendance/assessment edge cases after Dev 1 corrections. |

# 7. Evidence and communication sources

| Evidence source | Purpose |
| --- | --- |
| Weekly Recurring Client Meetings.docx - 24 September 2026 | Primary client-meeting transcript and prototype-review record. |
| Sprint 2 / Week 2 / Reshan Lahandapura - Developer 1 / Task 47 - Implementing Workshops 1-3 and assignment access.pdf | Evidence of two-of-three restriction behaviour and the interim workshop-completion limitation. |
| Sprint 2 / Week 2 / Reshan Lahandapura - Developer 1 / Task 48 - adding soft-deadline and hard deadline on assignment + others.pdf | Evidence of current assessment dates, resubmission, extension and grade-visibility configuration. |
| Sprint 2 / Week 2 / Walaa Ghanduri - UX Designer / Build review.pdf | UX review of the real Academy build and current site-level theming constraints. |
| OAPA_Brand_Book.docx | Brand baseline: OAPA signature treatment, Newsreader/Archivo typography and black/white visual rules. |
| Email to Vic - 24 September 2026 | Supervisor status update confirming no supervisor clarification was required that week and that the client meeting would proceed. |
| Email to Sam - 25 September 2026 | Site-level support request for automated/verifiable workshop attendance and OAPA Brand Book theming access. |

# 8. Task 41 acceptance mapping

| Task 41 acceptance item | Evidence in this record | Status |
| --- | --- | --- |
| Review prepared using real Week 1 OAPA implementation evidence. | Sections 1-2 use the real development course and Week 2 build evidence as the review baseline. | Met |
| Reusable course structure and progression reviewed. | Section 2 records the reusable shell and sequential restriction state. | Met |
| Workshop and assessment workflow position reviewed. | Sections 2-5 capture the two-of-three gate, attendance gap and assessment corrections. | Met |
| Learner tracking/self-check position reviewed. | Section 2 records progress, native Quiz and H5P status. | Met |
| UX and Brand Book position reviewed. | Sections 2, 4 and 5 record UX review and site-level branding work. | Met |
| Verified functionality separated from unresolved items. | Sections 2 and 5 distinguish working behaviour from partial/open items. | Met |
| Client/supervisor feedback and decisions recorded. | Sections 1, 3 and 4 record the client review and the supervisor status communication. | Met |
| Open questions/dependencies identified. | Section 5 lists the remaining implementation and site-level dependencies. | Met |
| Follow-up actions assigned. | Section 6 assigns role-owned follow-up actions. | Met |
| Review evidence saved and linked for handoff. | Section 7 lists the evidence sources to be linked from the Planner/Git handoff. | Met |

# 9. PM completion statement

Task 41 is complete. The Sprint 2 Week 2 stakeholder build review has been run against the real Academy implementation, the current prototype has been reviewed with the client, and the remaining workflow decisions have been converted into role-owned implementation actions. The project remains within the approved Core MVP scope. The key immediate dependencies are the final workshop-attendance mechanism, alignment of the assessment deadline workflow with the client decision, staff-side reporting verification, and site-level support for OAPA branding/theming.