Risk, Dependency, Escalation & Communication Register

Sprint 1 governance artifact - updated after current Academy access, client alignment and branding confirmation

| Project | P000785CSITCP / Group 74 Team A | Owner | Aryan Rajendra - Project Manager |
| --- | --- | --- | --- |
| Status | Updated / active register | Current as of | 5 September 2026 |

# 1. Current governance position

The original current-Academy access blocker is resolved. Sam created OAPA Academy accounts for Team 74 and the team confirmed that all five current-platform logins are working. Old Moodle reference access has also now been received and verified and remains reference-only. The client direction after the 24 August meeting with Michael Cowling and Jo-Anne Kelder remains the new Academy as the implementation target and a reusable branded course-template framework as the main project direction. The OAPA Brand Book has been received. Developer testing has now identified that the current Academy accounts do not provide the course-creation, configuration and plugin permissions needed for the Week 2 proof-of-concept work, so exact technical access and the final Sprint 2 Core MVP approval remain active dependencies.

Michael and Jo are continuing as the active OAPA project contacts for current decisions. Darryl advised on 21 August that he was in hospital, and this register does not assume a later availability change without evidence.

Evidence rule Current Academy access and old Moodle reference access are confirmed. Developer testing has identified missing course-creation, configuration and plugin permissions in the current Academy accounts. Where Sprint 1 proof-of-concept work is completed in an independent Moodle test environment, it must be clearly documented and re-verified in the OAPA Academy before the mechanism is treated as implementation-ready. No unverified technical assumption should be presented as a completed OAPA Moodle capability.

# 2. Active risk register

| ID | Type | Risk / issue | Status | Rating | Owner | Mitigation / next action |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Reference access | Old Moodle reference access received and verified | Resolved | Low | Aryan + Devs | Use the legacy Moodle for structure, content and plugin comparison only. Do not modify the reference platform. |
| R2 | Environment | Current Academy accounts do not provide the course-creation, configuration and plugin permissions needed for Week 2 proof-of-concept work | Active | Med-High | Reshan + Zarin + Aryan | Document the exact missing permissions and raise them through Sam / OAPA technical. Continue Sprint 1 feasibility work in a documented independent Moodle test environment where needed, then re-verify the selected mechanism in OAPA before Sprint 2 implementation is locked. |
| R3 | Stakeholder continuity | Primary contact availability changed during Sprint 1 | Mitigated | Medium | Aryan | Continue decisions through Michael and Jo, use Sam for technical access, do not rely on an assumed Darryl return date. |
| R4 | Schedule | Earlier access delay compressed Sprint 1 validation time | Active / managed | Med-High | Aryan | Prioritise Core MVP evidence, cross-role handoffs and playback readiness. Avoid expanding Sprint 1 into a full implementation sprint. |
| R5 | Scope | Broader OAPA target requirements may exceed the capstone Core MVP | Active | High | Aryan + Riley | Use the reusable-template direction as the organising goal, but require client and supervisor approval before locking the Sprint 2 implementation subset. |
| R6 | Alignment | BA, UX and technical findings may diverge if not cross-checked | Active | Medium | All / Aryan coordinates | Use the current scope baseline, client-meeting alignment document and role handoffs as one decision set. Resolve conflicts before playback. |
| R7 | Branding | Brand Book could be applied inconsistently or forced into irrelevant technical work | Controlled | Low | Walaa + Aryan | Use the Brand Book where learner-facing design decisions are made. Do not require unrelated BA or technical tasks to force branding content. |
| R8 | Assessment feasibility | Soft formative deadline and hard final deadline need a reliable Moodle workflow | Open | Med-High | Reshan + Zarin | Prototype or validate a clear Moodle mechanism that preserves formative feedback, revision and final submission behaviour before Core MVP commitment. |
| R9 | Workshop gating | Two-of-three workshop attendance rule and assessment gating need technical validation | Open | Med-High | Reshan + Zarin | Test how attendance or completion evidence can gate assessment access, document limitations and confirm the preferred approach with the client. |
| R10 | Workshop delivery | Client wants live online workshops within the system for international streams | Open | Medium | Devs + UX | Assess feasible Moodle-integrated workshop approach, time-zone handling and learner access. Do not overcommit before testing. |
| R11 | Micro-credentials | Short courses may not fit the standard 40-hour template without flexibility | Open | Medium | Riley + Walaa + Devs | Compare one configurable template against a separate short-course pattern and take the recommendation to client review. |
| R12 | Learner reporting | Login and progress tracking requirement is not yet defined to reporting-detail level | Open | Medium | Riley + Devs | Clarify who needs to see which activity, progress and at-risk indicators, then map to Moodle reporting capability. |
| R13 | Peer review | Anonymity, criteria and editorial workflow may require configuration decisions | Open | Medium | Riley + Devs | Assess suitable Moodle mechanisms and confirm the intended review visibility and outcomes with OAPA education stakeholders. |
| R14 | Quality | Current-state or feasibility claims could be recorded without evidence | Controlled | Medium | All / Aryan | Use screenshots, configuration notes, test results or other real Moodle evidence. Label anything not demonstrated as proposed or to be confirmed. |
| R15 | Confidentiality | OAPA specification and derivative project evidence are confidential | Controlled | Medium | All / Aryan | Keep confidential material in authorised project spaces and avoid publishing specification-derived confidential content to public repositories. |
| R16 | Approval | Sprint 2 Core MVP remains subject to Sprint 1 playback and client/supervisor alignment | Active | High | Aryan | Prepare the proposal and playback around the validated representative journey, record approvals and only then lock Sprint 2 implementation scope. |

# 3. Dependency register

| ID | Dependency | External / internal owner | Current state | Impact | Required action |
| --- | --- | --- | --- | --- | --- |
| D1 | Current Academy account access | Sam / OAPA technical | All five team logins verified working | Enables current-state audit and sandbox work | Resolved, keep account evidence |
| D2 | Old Moodle reference access | Sam / OAPA technical | Received and verified | Supports legacy structure, content and plugin comparison | Resolved, use reference-only and do not modify |
| D3 | Course-creation, plugin and change permissions | OAPA technical + Dev team | Developer testing shows current Academy accounts do not expose the permissions needed for the planned proof-of-concept work | Affects direct OAPA prototyping and Sprint 2 implementation approach | Use an independent Moodle test environment for Sprint 1 where required, document missing permissions and re-verify in OAPA before implementation |
| D4 | Core MVP and scope approval | Michael / Jo / Vic | Direction clarified, exact implementation subset still open | Controls Sprint 2 commitments | Confirm through Sprint 1 playback and record decision |
| D5 | OAPA Brand Book | Michael / OAPA | Received | Guides learner-facing visual direction | Use where relevant in UX and proposal work |
| D6 | Standard learner-cycle implementation | Dev team + client | Business rules confirmed, Moodle mechanisms partly open | Affects progression, workshops and assessment | Validate sequential unlock, attendance gating and assessment workflow |
| D7 | Micro-credential template approach | Michael / Jo + Team 74 | Need for shorter offerings confirmed, template pattern undecided | Affects reuse and architecture | Recommend configurable versus separate template |
| D8 | Representative course / exemplar | OAPA education contacts | Exact reference course not fully agreed | Affects Core MVP demonstration | Agree representative journey at playback/client review |
| D9 | Learner reporting detail | Michael / Jo + BA/Dev | Need for login and progress tracking confirmed, report detail open | Affects reporting configuration | Clarify required views, users and indicators |
| D10 | Team artifact alignment | All roles | Week 2 evidence streams must converge before playback | Prevents conflicting proposal decisions | Cross-check requirements, UX and technical evidence before sign-off |
| D11 | Recurring client cadence | Michael / Jo / Aryan | Michael and Jo confirmed Thursday 3.30 PM to 4.00 PM from 10 September. Jo advised she cannot attend 17 September, while the recurring meeting can still continue with Michael if available. | Supports ongoing decisions and feedback | Create the recurring Teams meeting and retain the agreed cadence |
| D12 | Sprint 1 playback booking | Vic / course process | Existing supervisor slot is Thursday 2.30 PM to 3.00 PM, playback booking method still needs clarification | Could affect formal Sprint 1 review timing | Confirm whether playback uses normal supervisor slot or separate booking |

# 4. Escalation path

| Trigger | Escalate to | Channel | Owner | Required record |
| --- | --- | --- | --- | --- |
| Routine client or project question | Michael Cowling + Jo-Anne Kelder | Email / agreed client meeting | Aryan PM | Record the decision or follow-up in Planner, project notes or the communication register. |
| Moodle access or permission issue | Sam via OAPA technical email | Email | Aryan PM, Developers provide technical detail | Provide specific evidence of the permission problem and escalate to Michael/Jo if it threatens Sprint 2 readiness. |
| Branding clarification | Michael / Jo | Email / client meeting | Aryan + Walaa | Use the Brand Book as the current reference and record any client clarification that changes the UX direction. |
| Scope or Core MVP conflict | Michael / Jo + Vic | Client / supervisor meeting | Aryan + Riley | Do not implement disputed scope, record the open decision and obtain approval. |
| Sprint 1 playback process unclear | Vic / relevant course support | Supervisor channel / email | Aryan PM | Confirm whether the playback occurs during the existing Thursday supervisor slot or requires a separate booking. |
| Project blocker threatens assessment or sprint delivery | Vic, Nhi, Alessio / course support | Supervisor email or meeting, PM channel, support route | Aryan PM | Provide dated evidence, impact and mitigation, avoid unsupported blame. |
| Internal team dependency or cross-test issue | Relevant role owner + PM | Teams + Planner | Aryan PM | Re-sequence work, use handoffs, and keep build and independent testing ownership separate where required. |

# 5. Communication and evidence register

| Date | Event | People / channel | Outcome / current state | Evidence |
| --- | --- | --- | --- | --- |
| 11 Aug 2026 | Initial client meeting | Darryl Clare + Team 74 | Original learner-experience focus confirmed, backend already established, access and sandbox approach discussed. | Meeting / proposal evidence |
| 14-19 Aug 2026 | Access follow-up and escalation | Darryl, course contacts, Team 74 | Access remained unavailable, team continued research and recorded the blocker rather than idling. | Email / Teams / support evidence |
| 21 Aug 2026 | OAPA continuity and specification | Michael, Darryl, Jo | Michael explained the continuity situation, Darryl confirmed hospitalisation, Jo supplied the detailed OAPA Moodle specification and technical access route. | Email + specification |
| 21 Aug 2026 | Moodle access request | Sam / OAPA technical | Requested access to both the current Academy and the old Moodle reference platform. | Sent email |
| 24 Aug 2026 | Client alignment meeting | Michael, Jo, Team 74 | Confirmed new Academy as the work target, old Moodle as reference only, reusable template as the main value direction, standard learner cycle, sequential progression, workshop requirement, learner tracking, branding and micro-credential flexibility questions. | Meeting recording + transcript |
| 24 Aug 2026 | Current Academy account setup | Sam / OAPA technical | Sam created current Academy accounts for the team and advised that old Moodle access would be handled separately. | Email |
| 25 Aug 2026 | Current Academy access verification | Team 74 / Sam | Team confirmed that all five current Academy logins were working correctly. | Email reply + team update |
| 26 Aug 2026 | OAPA Brand Book received | Michael Cowling / Team 74 | Brand Book supplied after the agreed reminder and added as the current branding reference for relevant UX and proposal work. | Email attachment / Teams update |
| Weekly | Supervisor governance | Vic Ciesielski | Recurring Thursday 2.30 PM to 3.00 PM supervisor slot used for sprint progress, decisions and blockers. | Calendar / Teams meeting |
| 1 Sep 2026 | Recurring client meeting request | Michael + Jo / Team 74 | PM asked whether a weekly Thursday client check-in could be scheduled for the remainder of the project. | Email |
| 2 Sep 2026 | Client meeting availability responses | Michael Cowling + Jo-Anne Kelder | Michael and Jo confirmed the recurring Thursday 3.30 PM to 4.00 PM client-meeting time from 10 September. Jo noted she cannot attend 17 September, but the recurring session can continue with Michael if available. | Email |
| 2 Sep 2026 | Non-technical supervisor check-in | Leon / Team 74 | PM advised that the project is progressing smoothly with no current non-technical blocker and asked how to book if a session is still required. | Email |

# 6. Communication rules for the team

Aryan as PM remains the single coordination point for external stakeholder follow-ups unless another member is specifically asked to respond.

Important client and supervisor decisions are summarised in Teams and reflected in Planner or project decision records so the team works from one version of truth.

No task is marked complete until its checklist is genuinely satisfied and a completion note, handoff and real evidence link are recorded.

The new Academy is the implementation target. The legacy Moodle is reference-only and should not be changed by Team 74.

Developer work should include cross-build and cross-testing ownership so each developer both configures or builds and independently validates the other developer's work.

Current-state claims and technical feasibility claims must be backed by real Moodle evidence. Anything not demonstrated remains proposed, under test or to be confirmed.

The confidential OAPA specification and derivative confidential evidence remain in authorised project spaces.

# 7. Immediate action list

| ID | Action | Owner | Status |
| --- | --- | --- | --- |
| A1 | Document the exact missing new Academy course-creation, plugin, configuration and safe-change permissions, raise the access need through Sam / OAPA technical, and use a documented independent Moodle test environment for Sprint 1 proof-of-concept work where required. | Reshan + Zarin + Aryan | In progress |
| A2 | Use the verified old Moodle reference access only for comparison of course structure, content and useful plugin patterns. Do not modify the legacy platform. | Aryan + Devs | Resolved |
| A3 | Use the received Brand Book in relevant UX and proposal decisions, without forcing it into unrelated role work. | Walaa + Aryan | In progress |
| A4 | Complete Week 2 requirements, UX and developer proof-of-concept evidence and cross-check the findings before playback. | All role owners | In progress |
| A5 | Consolidate the Sprint 1 client proposal and proposed Core MVP around the validated reusable-template direction. | Aryan + Riley | In progress |
| A6 | Create the recurring Thursday 3.30 PM to 4.00 PM client meeting from 10 September now that Michael and Jo have confirmed the time. | Aryan | Ready to schedule |
| A7 | Clarify whether the Sprint 1 Playback uses the existing Thursday supervisor slot or requires a separate booking. | Aryan | Open |
| A8 | Prepare Sprint 1 playback evidence, decision requests and the draft Sprint 2 implementation plan. | Aryan + Team | Open |

# 8. Planner acceptance checklist mapping

| Checklist item | Evidence in this artifact |
| --- | --- |
| Michael and Jo recorded as current main client contacts | Satisfied, Sections 1, 3, 4 and 5 reflect the current client continuity path. |
| New Academy recorded as implementation target | Satisfied, Sections 1 and 6 record the new Academy as the target environment. |
| Legacy Moodle recorded as reference-only | Satisfied, D2 and team communication rules keep legacy access separate from implementation. |
| Current Academy access status recorded accurately | Satisfied, D1 and the communication register record that all five logins are working. |
| Reusable branded course template recorded as main direction | Satisfied, Section 1 and the current risk/dependency treatment use the reusable-template direction as the organising project goal. |
| Confirmed learner-cycle rules reflected | Satisfied, R8-R10 and D6 reflect sequential progression, workshops, assessment and related mechanism risks. |
| Remaining dependencies retained without unsupported claims | Satisfied, technical permissions, micro-credential flexibility, reporting, playback and Core MVP approval remain explicitly open, while old Moodle reference access is recorded as resolved. |

# 9. PM completion note for this update

This update closes the earlier current-Academy access blocker because the team has verified that its current-platform logins work. It also replaces the earlier branding uncertainty with the received OAPA Brand Book and records the clarified new-platform, reusable-template and learner-cycle direction from the 24 August client meeting.

The register now records old Moodle reference access as resolved. It intentionally keeps the Academy permission issue, implementation mechanisms and Sprint 2 Core MVP approval open until the required access is provided, technical findings are re-verified in OAPA, or the relevant decisions are formally agreed.