# Sprint 2 Week 3 Governance & Evidence Closeout Record

Task 51 - Consolidate Sprint 2 evidence, decisions, defects and open site-level dependencies against the Planner and Core MVP baseline

| Project | P000785CSITCP / Group 74 - Team A | Owner | Aryan Rajendra - Project Manager |
| --- | --- | --- | --- |
| Status | Final / Task 51 completion evidence | Current as of | 4 October 2026 |

# 1. Purpose and closeout context

This record closes Sprint 2 governance for Team 74 by consolidating the final Core MVP evidence, stakeholder decisions, Week 3 validation/fix results, remaining environment-level dependencies and the exact items handed into Sprint 3. It reflects the completed Sprint 2 Week 3 Planner work and the current project position at closeout.

Sprint 2 has delivered the representative reusable OAPA Academy learner journey that was committed at the end of Sprint 1. All non-access-blocked Sprint 2 work is treated as complete. Items that still require OAPA-controlled site-level capability are not misrepresented as completed implementation; they are explicitly carried into Sprint 3 with evidence, owners and a defined route for completion.

Scope control: Sprint 2 closes on the agreed Core MVP. The remaining work is refinement and environment-level completion, not a new feature-expansion sprint. The isolated/sanitised Academy copy and relevant site-level capability are the active external dependency for the remaining attendance, branding and navigation/accessibility implementation.

# 2. Sprint 2 final delivery position

| Closeout area | Final status | Evidence / current state | Sprint 3 treatment |
| --- | --- | --- | --- |
| Reusable course framework | Delivered / working | Course Home, Modules 1-3, Workshops 1-3 and Assessment are implemented in Team 74 - Course Development as the representative reusable pattern. | Carry forward only reuse hardening/documentation. |
| Sequential learner progression | Delivered / working | Completion and restricted-access behaviour has been demonstrated in Student view with visible locked/unlocked states. | Regression-test after site-level refinements. |
| Workshop eligibility logic | Delivered / logic working | Any valid two-of-three workshop combination can satisfy the existing Assessment restriction logic. | Replace the interim completion source with the final verified attendance mechanism in Sprint 3. |
| Workshop attendance source | Open / site-level dependency | Client requires verifiable MS Teams attendance, preferably automated where supported, with facilitator override. | Complete once isolated copy/integration capability is available. |
| Assessment workflow | Delivered / validated representative flow | Soft feedback/revision, final submission, extension and grade-visibility behaviour have been implemented/tested to the current Academy capability and documented through Week 2-3 evidence. | Final regression alongside verified attendance/eligibility. |
| Self-check / interactivity | Delivered with native fallback | Moodle-native Quiz/self-check supports the Core MVP. H5P remains optional and does not block delivery; final H5P/native-fallback position is documented by Dev 2. | Retain native pattern unless OAPA chooses H5P. |
| Completion / tracking / reporting | Delivered at current role capability | Student completion/progress and staff-side evidence were cross-tested through the Sprint 2 QA tasks. | Final release regression in Sprint 3. |
| OAPA branding / fonts | Open / site-level dependency | Brand Book rules are defined and UX handoff is complete; Newsreader/Archivo and Academy-wide theme treatment require site-level support. | Implement in isolated copy when capability is provided. |
| Navigation / accessibility refinements | Partially complete / site-level remainder | Course-level UX/accessibility review and fixes are complete; remaining site-level navigation refinements require the isolated environment. | Implement and regression-test in Sprint 3. |
| Reuse / admin handoff | Delivered as documented workflow | Content-expert steps and OAPA-admin handoff boundaries are documented; reuse is to be proven on a copy without altering the master pattern. | Re-verify in isolated copy during Sprint 3. |

# 3. Week 3 evidence consolidation

| Tasks | Owner | Work package | Closeout evidence position | Status |
| --- | --- | --- | --- | --- |
| T51 | Aryan Rajendra / PM | Governance and evidence closeout | This record consolidates final Sprint 2 delivery, decisions, defects, dependencies and evidence position. | Complete |
| T52 | Aryan Rajendra / PM | Playback and Sprint 3 handover | Playback deck, speaker notes and the Sprint 3 refinement plan/backlog prepared with all remaining actions assigned. | Complete |
| T53-54 | Riley Pittard / BA | Final acceptance + gap prioritisation | Final learner/reuse acceptance review completed; pass/fail/open items and Sprint 3/deferred scope separated. | Complete |
| T55-56 | Walaa Ghanduri / UX | Final UX/accessibility + branding/navigation handover | Final real-build UX review completed; approved refinement items prepared, including Participants-page refinement evidence and site-level branding/navigation needs. | Complete |
| T57-58 | Reshan Lahandapura / Dev 1 | Defect fixing/regression + reuse/admin handover | Structural/progression/workshop/assessment fixes completed where current access permits; reuse/admin handoff path documented. Task 57 evidence is stored in the Week 3 repository. | Complete |
| T59-60 | Shaikh Zarin Tasnim / Dev 2 | Independent regression + quality closeout | Final browser/device/accessibility/regression and interactivity/tracking quality closeout completed against the current environment, with remaining site-level assumptions explicitly recorded. | Complete |

# 4. Final defects, dependencies and carry-forward decisions

| ID | Item | Status | Closeout rationale | Owner | Next action |
| --- | --- | --- | --- | --- | --- |
| C1 | Isolated/sanitised Academy copy + site-level capability | Open / external | Current Teacher access cannot safely expose every theme/integration/site-level control needed for final refinements. | Aryan / Sam / OAPA | Client-supported isolated-copy route requested; expected next access step from Monday 5 October 2026. |
| C2 | Verified MS Teams workshop attendance | Open / dependent on C1 | 2-of-3 restriction logic works, but the final attendance source must be verifiable and support facilitator override. | Reshan + Riley + Aryan | Implement preferred supported integration or documented verified Teams-report + facilitator-controlled Moodle fallback. |
| C3 | OAPA fonts and Academy-wide branding | Open / dependent on C1 | Brand rules and UX handoff are complete; site-level application remains outside normal Teacher controls. | Walaa + Zarin + Aryan | Apply Newsreader/Archivo and approved black/white treatment in isolated copy where supported. |
| C4 | Site-level navigation/accessibility refinement | Open / dependent on C1 | Course-level fixes are complete; remaining navigation/theme refinements require broader capability. | Walaa + Devs | Implement only feasible/approved refinements and regression-test. |
| C5 | H5P Question Set | Closed as non-blocking | H5P is optional. Moodle-native Quiz/self-check satisfies the Core MVP even if H5P remains unavailable or unnecessary. | Zarin | Document final status; do not block Sprint 3 or replace working native functionality without reason. |
| C6 | Scope/deferred requirements | Managed | Peer review and wider Academy/admin items are not silently treated as delivered Core MVP behaviour. | Riley + Aryan | Keep delivered/deferred/OAPA-admin scope explicit in Sprint 3 acceptance and final handover. |

# 5. Stakeholder and governance events closing Sprint 2

| Date | Event | Decision / evidence outcome |
| --- | --- | --- |
| 1 Oct 2026 | Client closeout meeting - 1h 09m | Reviewed development evidence, remaining implementation, access constraints and the isolated-copy route. Remaining work was framed as refinement/site-level completion rather than a new Core MVP. |
| 1 Oct 2026 | Vic dual-role review - 30 min | Vic, acting as both supervisor and technical advisor, reviewed Sprint 2 closeout, blockers and Sprint 3 direction. |
| 2 Oct 2026 | Internal team meeting - 42 min | Reconciled the specification, workshop integration, access needs, role boundaries and Sprint 3 refinement plan. |
| 3 Oct 2026 | Access-copy follow-up | Client-supported route progressed: request an isolated Academy copy with the site-level capability required for the remaining blocked work. |
| 4 Oct 2026 | Sprint 2 PM closeout | All non-access-blocked Week 3 work treated as complete; open site-level dependencies transferred to Sprint 3 with owners and evidence expectations. |

# 6. Task 51 acceptance mapping

| Task 51 acceptance item | Evidence in this record | Status |
| --- | --- | --- |
| Sprint 2 evidence consolidated against Planner/Core MVP baseline. | Sections 2-3 summarise final delivery and role-owned Week 3 evidence. | Met |
| Key stakeholder decisions remain traceable. | Sections 4-5 preserve the client/Vic closeout decisions and implementation consequences. | Met |
| Defects and limitations are visible rather than hidden. | Section 4 records every material carry-forward item and why it remains open. | Met |
| Site-level dependencies are separated from course-level work. | C1-C4 distinguish external OAPA capability from completed Core MVP logic. | Met |
| Resolved/non-blocking issues are closed accurately. | C5 records H5P as optional/non-blocking with the native fallback preserved. | Met |
| Every remaining action has an owner and next action. | Section 4 assigns owners and Sprint 3 action for each open item. | Met |
| Week 3 task/evidence position is complete and traceable. | Section 3 maps T51-T60 and current repository evidence. | Met |
| Sprint 2 closes without hidden scope expansion. | Scope-control callout plus C6 preserve the accepted Core MVP boundary. | Met |

# 7. PM completion statement

Task 51 is complete. Sprint 2 evidence, decisions, final Week 3 validation/fix work and outstanding dependencies are consolidated into one closeout position. The reusable Core MVP is complete wherever current Academy access permits. The remaining implementation is specifically limited to the isolated-copy/site-level path for verified workshop attendance, OAPA branding/fonts and navigation/accessibility refinements, plus final Sprint 3 regression and handover. These items are visible, owned and transferred forward rather than being treated as hidden or incomplete Sprint 2 work.