Sprint 3 Week 2 Governance, Risk and Evidence Control Record

Task 72 - Sprint 3 Governance Risk & Evidence Control

| Project number | 74 |
| --- | --- |
| Project ID | P000785CSITCP |
| Project name | Building an Editor Academy Moodle platform |
| Client / organization | Open Access Publishing Association (OAPA) |
| Team | Team A |

Task and closeout position

| Role | PM - Aryan Rajendra | Date | 18/10/2026 |
| --- | --- | --- | --- |
| Sprint / Week | Sprint 3 / Week 2 | Hours | 2 |
| Track | Design / Product | Status | Finished |
| Planner task | Task 72 | Planned minutes | 120 |
| Sprint purpose | Refine / finalise release candidate | Delivery blocker | None |

1. Purpose and completion position

This record closes Sprint 3 Week 2 governance by reconciling Planner, CRM/project timeline, the Master Document, current repository artefacts, Week 1 defects, Week 2 fixes, independent acceptance evidence and the external OAPA environment position. The purpose is to leave a truthful final-week baseline: all Week 2 tasks are complete, no current blocker prevents delivery, and every remaining acceptance issue or external action is explicit.

The local Moodle template is the project release/handover baseline. Sam Perry reported complications finalising the isolated Academy development instance, but Michael/OAPA clarified that Team 74 can submit the completed template as the final artefact. If the isolated instance arrives before handover the team will transfer/reproduce and revalidate the work there; if not, the project proceeds from the localised copy without delaying handover.

2. Sprint 3 Week 2 governance baseline

Tasks 71-80 are the approved Sprint 3 Week 2 workload and are complete at closeout.

Every team member retained two 120-minute tasks for 240 planned minutes; the Week 2 team plan therefore remained 20 planned team-hours.

Week 2 remained a Refine MVP week: work focused on audit/fixes, user-story acceptance, UX/accessibility, branding/navigation and Participants rather than unapproved feature expansion.

The local Moodle implementation is the release baseline and the isolated OAPA environment is an optional final validation/deployment route rather than a delivery blocker.

Independent acceptance evidence is authoritative for what has and has not been proven. Completed Developer tasks do not automatically mean every user story has passed.

Week 3 is preserved for final retest/classification, documentation, playback, optional environment transfer and handover.

3. Planner, CRM, Master Document and repository reconciliation

| Governance surface | Week 2 closeout position | Control |
| --- | --- | --- |
| Planner | Tasks 71-80 complete; two tasks per member at 120 minutes each. | Keep the final task titles, completion notes, checklist evidence and ownership aligned with repository artefacts. |
| CRM / Project Timeline | Week 2 team, client, supervisor and OAPA-environment communications are recorded with dates, attendees/outcomes and next actions. | Use the CRM as the communication chronology; do not duplicate or invent stakeholder decisions elsewhere. |
| Master Document | Week 2 entries are complete except PM evidence URLs awaiting commit links. | Update only the PM Task 71/72 evidence links after Git commit; preserve other members' submitted completion text. |
| Repository | All eight non-PM Week 2 deliverables are present; PM Task 71/72 records complete the role-owned set. | Commit PM artefacts into Sprint 3/Week 2/Aryan Rajendra - Project Manager and use those commit URLs in Planner/Master. |
| Environment / handover | Local Moodle is the release baseline; isolated OAPA environment remains optional for final transfer/revalidation. | Do not delay final handover if the isolated instance is unavailable. |

4. Defect and acceptance reconciliation

| Task | Owner | Week 2 purpose | Planned | Closeout state |
| --- | --- | --- | --- | --- |
| 71 | Aryan Rajendra | Stakeholder implementation review and final refinement decisions | 120 min | Finished |
| 72 | Aryan Rajendra | Governance, risk, evidence reconciliation and Week 3 baseline | 120 min | Finished |
| 73 | Riley Pittard | Final Student/Facilitator user stories and acceptance baseline | 120 min | Completed |
| 74 | Riley Pittard | Independent functional acceptance against the final stories | 120 min | Completed |
| 75 | Walaa Ghanduri | UX / brand / navigation review work | 120 min | Completed |
| 76 | Walaa Ghanduri | WCAG 2.2 accessibility guidance / UX audit closeout | 120 min | Completed |
| 77 | Reshan Lahandapura | Full-template functional/configuration audit | 120 min | Completed |
| 78 | Reshan Lahandapura | Audit defect fixes and corrected-candidate handoff | 120 min | Completed |
| 79 | Shaikh Zarin Tasnim | Branding/navigation/accessibility defect closure | 120 min | Completed |
| 80 | Shaikh Zarin Tasnim | Participants/responsive/technical-quality hardening | 120 min | Completed |

5. Risk and dependency register

| Risk / dependency / acceptance item | Week 2 closeout position | Owner / final-week action |
| --- | --- | --- |
| F01 - M1 H5P blank/stale completion state | Reproduced by independent BA acceptance; saved attempts exist but visible end state is unreliable until reload. | Reshan + Zarin/setup owner + Riley - triage and retest; retain native Quiz fallback. |
| F02 - course Gradebook recalculating | Attempts reports work, but course Grades remains unusable in the tested local candidate. | Reshan/setup owner + Riley - investigate local processing/setup and retest; classify honestly if environment-specific. |
| F03 - assignment grading interface does not load | Blocks final marking/release and dependent feedback/revision acceptance. | Reshan/setup owner + Riley - triage and retest Teacher marking, feedback/revision and release. |
| D4 / attendance exception distinction and policy | Still open; Late/Excused/source/exception policy is not fully approved or independently covered. | BA + client/content owner + Dev 1 - resolve if confirmed, otherwise hand over as policy/configuration item. |
| D6 / workshop production timing and D8 content names | Implementation placeholders/content-owned values remain outside final technical proof. | Content/facilitator owner - replace with real dates/times/names during deployment or content handover. |
| D10 / H5P blue Check button | Known iframe/site-style limitation; functional native Quiz fallback exists. | OAPA admin/content owner - choose H5P as-is, site-level styling if supported, or native Quiz fallback. |
| Isolated OAPA development environment | Sam reported complications; not a project blocker because local-template handover is accepted. | PM + OAPA/Development - transfer/revalidate only if available before handover. |

6. Evidence expectations and closeout controls

All ten Week 2 tasks have one scored owner, 120 planned minutes, completion notes and a repository artefact or evidence source. PM Task 71 and Task 72 closeout documents complete the Week 2 repository set.

The CRM/project timeline records the Monday 1 hour 5 minute team meeting, Thursday 33 minute 42 second team meeting, the 15 October OAPA client review, the 15 October Vic review, and the Sam/OAPA environment communication and contingency.

The Master Document is reconciled to the same Week 2 task titles, status, deliverables and completion position. PM evidence links remain blank until the two final PM artefacts are committed.

Riley's independent Task 74 result remains the acceptance boundary: F01-F03 and Open/Dependency items are carried forward and are not silently marked closed because implementation tasks are complete.

Any Week 3 correction or OAPA transfer must preserve the existing evidence history rather than rewriting Week 2 results.

7. Final Week 3 action baseline

| Control | Week 2 closeout decision |
| --- | --- |
| Sprint definition | Sprint 3 Week 2 remained refinement/acceptance work; no unapproved feature expansion was introduced. |
| Completion vs acceptance | All Planner tasks can be complete while independent release acceptance still contains Fail/Open/Dependency results; both states are recorded separately. |
| Environment contingency | The local Moodle template is sufficient for final artefact handover; isolated OAPA access is optional final transfer/validation. |
| Evidence discipline | Planner, CRM, Master Document and repository artefacts must describe the same implementation and acceptance state. |
| Final week | Week 3 is reserved for retest/classification, final documentation, near-final playback, handover and optional OAPA transfer. |

8. Completion statement

Task 72 is complete. Planner, CRM/project timeline, Master Document and repository evidence now describe the same Sprint 3 Week 2 position: all role-owned tasks are complete within the approved workload, the local Moodle template provides a valid path to handover, and no current external access blocker prevents project completion. Remaining functional acceptance failures, incomplete coverage, policy/content decisions and optional OAPA-environment validation are explicitly assigned to final-week retest, classification and handover so no hidden defect or unowned dependency is carried forward.

Repository target: Sprint 3/Week 2/Aryan Rajendra - Project Manager/Sprint3Week2GovernanceRiskEvidenceControlRecord.docx