## Instructions
Sprint Planning — Instructions & Legend
COSC2408 Programming Project 1
What this workbook is for
This is the detailed HOW for next sprint — the task-by-task breakdown, owner, timing and sequencing. It is a separate deliverable from your Sprint Playback slide 7 ("What's Next"), which only states WHAT you're promising. This workbook is where that promise gets broken down into real, assigned, time-estimated tasks.
The 240-minute rule
Every team member must be assigned at least 240 minutes (4 hours) of tasks per week, for every week of the upcoming sprint. Estimate time at a junior-practitioner level — the same standard used for your weekly task board (e.g. a straightforward API endpoint with tests is ~30 minutes, regardless of how long it actually takes you in practice). The Weekly Workload Check tab totals this automatically and flags anyone under the minimum.
How to use the Task Plan & Gantt tab
1. Delete the yellow example row once you understand the format — it is not a real task.
2. Add one row per task: name it, assign an Owner, estimate the minutes, set the Week (1–3), the Start Day WITHIN that week (1 = Monday, 5 = Friday) and the Duration in days.
3. The Gantt bar on the right fills in automatically based on Start Day and Duration — you don't edit it directly.
4. Use Dependencies to note if a task can't start until another Task ID is done.
5. Update Status as the sprint progresses — this tab doubles as your working plan, not just a one-off submission.
Editable vs computed
Only the white cells in the Task Plan & Gantt tab are for you to fill in (Task ID through Status). The Gantt bars and everything on the Weekly Workload Check tab are computed automatically — don't type into them. You can change the roles by maunally typing into Column C (owner) and then using the same valueein the Weekly Workload check
Submission
Rename this file x - team name - S1W7_ganttplan (e.g. 90 - Food Delivery System - S1W7_ganttplan) and submit alongside your other Week 7 files. It plans the upcoming sprint, so it's due the same week as your Playback.
Colour key
Example row — delete before submitting
Weekly Workload Check: meets the 240-minute minimum
Weekly Workload Check: under the 240-minute minimum

## Task Plan & Gantt
Team 74 — Next-Sprint Task Plan & Gantt ¦ Sprint 2 (Weeks 1–3)
Every member needs ≥240 min/week. See the Instructions tab before editing.
Task ID | Task Name | Owner | Est. Minutes | Week | Start Day (1=Mon–5=Fri) | Duration (days) | Dependencies | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
[8 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
T31 | [SPRINT 2 GOVERNANCE & IMPLEMENTATION CONTROL] - Task 31 Initialise the Sprint 2 Core MVP in Planner/Gantt; assign role tasks, evidence expectations and review checkpoints: 90 | Aryan Rajendra | 90 | 1 | 1 | 1 | -
T32 | [SPRINT 2 GOVERNANCE & CLIENT/SUPERVISOR CONTROL] - Task 32 Update the Sprint 2 risk/decision baseline and prepare client/supervisor review plus the route for exact OAPA site-level requests: 150 | Aryan Rajendra | 150 | 1 | 2 | 4 | T31
T33 | [SPRINT 2 CORE MVP REQUIREMENTS CONTROL] - Task 33 Convert the approved Core MVP acceptance criteria into build/test checks for course structure, progression, tracking and reuse: 120 | Riley Pittard | 120 | 1 | 1 | 1 | -
T34 | [SPRINT 2 REQUIREMENTS & DECISION CONTROL] - Task 34 Confirm and record Week 1 requirement decisions for workshops, assessment, reporting and any peer-review scope; hand off unresolved items: 120 | Riley Pittard | 120 | 1 | 2 | 2 | T33
T35 | [SPRINT 2 UX IMPLEMENTATION HANDOFF] - Task 35 Issue the Moodle-ready UX handoff for Course Home, module layout, navigation/signposting and current OAPA Brand Book rules: 150 | Walaa Ghanduri | 150 | 1 | 1 | 1 | -
T36 | [SPRINT 2 UX FEASIBILITY & ACCESSIBILITY] - Task 36 Map the approved UX to real Academy constraints with development; flag theme/site-level needs and accessible course-level alternatives: 90 | Walaa Ghanduri | 90 | 1 | 2 | 2 | T35
T37 | [SPRINT 2 REUSABLE COURSE BUILD] - Task 37 Configure the reusable course shell in the OAPA dev course: Course Home, Modules 1–3, Workshops 1–3 and Assessment placeholders: 150 | Reshan Lahandapura | 150 | 1 | 2 | 1 | T33,T35
T38 | [SPRINT 2 PROGRESSION & COMPLETION] - Task 38 Configure sequential completion/restricted access and the visible progress pattern; capture Student-view evidence of lock/unlock behaviour: 90 | Reshan Lahandapura | 90 | 1 | 3 | 1 | T37
T39 | [SPRINT 2 INTERACTIVITY & TRACKING] - Task 39 Configure a representative self-check/tracking pattern using Moodle-native capability; use H5P only if the OAPA issue is resolved: 120 | Shaikh Zarin Tasnim | 120 | 1 | 3 | 1 | T33,T37
T40 | [SPRINT 2 CROSS-TESTING & QUALITY] - Task 40 Independently cross-test the course structure and progression in Student view; log defects across incomplete and returning-learner states: 120 | Shaikh Zarin Tasnim | 120 | 1 | 4 | 2 | T38,T39
T41 | [SPRINT 2 BUILD REVIEW & STAKEHOLDER ALIGNMENT] - Task 41 Run the mid-sprint client/supervisor build review and record decisions, open items and agreed follow-up actions: 120 | Aryan Rajendra | 120 | 2 | 1 | 2 | T38,T40
T42 | [SPRINT 2 GOVERNANCE & TECHNICAL ESCALATION] - Task 42 Update Planner, risks and dependencies after review; raise only specific evidenced OAPA site-level requests that block approved requirements: 120 | Aryan Rajendra | 120 | 2 | 3 | 3 | T41
T43 | [SPRINT 2 CORE MVP VALIDATION] - Task 43 Validate the Week 1 build against the Core MVP acceptance criteria and record pass/fail results, gaps and required fixes: 120 | Riley Pittard | 120 | 2 | 1 | 1 | T38,T40
T44 | [SPRINT 2 REQUIREMENTS & WORKFLOW DEFINITION] - Task 44 Finalise implementation criteria for the two-of-three workshop gate, formative-to-final assessment, reporting and any approved peer-review behaviour: 120 | Riley Pittard | 120 | 2 | 2 | 1 | T43
T45 | [SPRINT 2 UX BUILD REVIEW] - Task 45 Review the real Academy build against the approved learner journey and OAPA Brand Book; issue prioritised UX corrections: 120 | Walaa Ghanduri | 120 | 2 | 1 | 1 | T38,T40
T46 | [SPRINT 2 UX ACCESSIBILITY & NAVIGATION] - Task 46 Run an accessibility, navigation and signposting pass on implemented flows and hand off feasible course-level corrections: 120 | Walaa Ghanduri | 120 | 2 | 2 | 2 | T45
T47 | [SPRINT 2 WORKSHOP & ELIGIBILITY IMPLEMENTATION] - Task 47 Implement Workshops 1–3 and the validated two-of-three assessment-eligibility approach, including workshop communication elements where supported: 150 | Reshan Lahandapura | 150 | 2 | 3 | 1 | T43,T44,T45
T48 | [SPRINT 2 ASSESSMENT WORKFLOW IMPLEMENTATION] - Task 48 Implement the representative soft-deadline feedback/revision to hard-deadline final assessment workflow, rubric and grade-visibility behaviour where feasible: 90 | Reshan Lahandapura | 90 | 2 | 3 | 1 | T44
T49 | [SPRINT 2 TRACKING & REPORTING VERIFICATION] - Task 49 Verify learner completion/progress/reporting plus workshop and assessment access rules; capture Student and staff-side evidence: 120 | Shaikh Zarin Tasnim | 120 | 2 | 4 | 1 | T47,T48
T50 | [SPRINT 2 WORKFLOW CROSS-TESTING & EDGE CASES] - Task 50 Cross-test workshop/assessment edge cases including incomplete attendance, direct hard-deadline submission, revision, extensions and returning learners: 120 | Shaikh Zarin Tasnim | 120 | 2 | 5 | 1 | T48,T49
T51 | [SPRINT 2 GOVERNANCE & EVIDENCE CLOSEOUT] - Task 51 Consolidate Sprint 2 evidence, decisions, defects and open site-level dependencies against the Planner and Core MVP baseline: 120 | Aryan Rajendra | 120 | 3 | 1 | 1 | T47,T48,T49,T50
T52 | [SPRINT 2 PLAYBACK & SPRINT 3 HANDOVER] - Task 52 Prepare the Sprint 2 playback/client review and Sprint 3 refinement backlog/handover with every remaining action assigned: 120 | Aryan Rajendra | 120 | 3 | 3 | 3 | T51
T53 | [SPRINT 2 FINAL ACCEPTANCE VALIDATION] - Task 53 Run the final end-to-end acceptance review of the representative learner journey and the content-expert reuse process: 120 | Riley Pittard | 120 | 3 | 1 | 1 | T47,T48,T49,T50
T54 | [SPRINT 2 GAP & REFINEMENT PRIORITISATION] - Task 54 Record final pass/fail/open gaps and prioritise accepted Sprint 3 refinements or deferred requirements without expanding Core MVP scope: 120 | Riley Pittard | 120 | 3 | 3 | 2 | T53
T55 | [SPRINT 2 FINAL UX & ACCESSIBILITY REVIEW] - Task 55 Complete the final UX/accessibility review across Course Home, modules, workshops, assessment and learner progress: 120 | Walaa Ghanduri | 120 | 3 | 1 | 1 | T47,T48,T49,T50
T56 | [SPRINT 2 BRANDING & UX HANDOVER] - Task 56 Validate final branding/navigation consistency and prepare the UX handover for Sprint 3 refinement and final documentation: 120 | Walaa Ghanduri | 120 | 3 | 3 | 2 | T55
T57 | [SPRINT 2 DEFECT FIXING & REGRESSION] - Task 57 Fix structural, progression, workshop and assessment defects from final acceptance/UX review and regression-test the corrected behaviours: 120 | Reshan Lahandapura | 120 | 3 | 2 | 2 | T53,T55
T58 | [SPRINT 2 REUSE & ADMIN HANDOVER] - Task 58 Verify reusable-template/content-expert reuse and document the OAPA-admin duplication/site-level handoff path without altering the master pattern: 120 | Reshan Lahandapura | 120 | 3 | 4 | 2 | T57
T59 | [SPRINT 2 QUALITY & REGRESSION TESTING] - Task 59 Run the final browser/device/accessibility/regression pass and independently re-test Dev 1 fixes from Student and Teacher views: 120 | Shaikh Zarin Tasnim | 120 | 3 | 4 | 1 | T53,T55,T57
T60 | [SPRINT 2 INTERACTIVITY & QUALITY CLOSEOUT] - Task 60 Close interactivity/tracking evidence, including current H5P status or native fallback, defect results, environment assumptions and quality handoff: 120 | Shaikh Zarin Tasnim | 120 | 3 | 5 | 1 | T59

## Weekly Workload Check
Weekly Workload Check — 240 min (4 hrs) minimum per person, per week
Computed automatically from the Task Plan & Gantt tab. Do not edit the numbers directly.
Role | Week 1 (min) | Week 2 (min) | Week 3 (min) | Sprint Total (min) | Sprint Total (hrs)
Aryan Rajendra | 240 | 240 | 240 | 720 | 12
Reshan Lahandapura | 240 | 240 | 240 | 720 | 12
Shaikh Zarin Tasnim | 240 | 240 | 240 | 720 | 12
Walaa Ghanduri | 240 | 240 | 240 | 720 | 12
Riley Pittard | 240 | 240 | 240 | 720 | 12
Green = meets the 240-minute weekly minimum. Red = under the minimum — rebalance tasks in the Task Plan & Gantt tab.